This Annexure shall be completed and issued as part of the tender documents and, subject to any amendments to be incorporated into the Contract, is to be attached to the General Conditions of Contract and shall be read as part of the Contract.

Item

| 1 | Principal (clause 1) X ACN | Shire of Denmark |
| --- | --- | --- |
| 2 | Principal’s address | 953 South Coast Highway Denmark 6333 |
| 3 | Contractor (clause 1) X ACN | To be confirmed |
| 4 | Contractor’s address | To be confirmed |
| 5 | Superintendent (clause 1) X ACN | Person nominated by the Principal |
| 6 | Superintendent’s address | 953 South Coast highway Denmark 6333 |
| 7 | - Date for practical completion (clause 1) X OR - Period of time for practical completion (clause 1) X | The Works Under Contract (WUC) shall be completed by 24 March 2027. |
| 8 | Governing law (page 5, clause 1(h))X | Western Australia If nothing stated, that of the jurisdiction where the site is located X |
| 9 | - Currency (page 5, clause 1(g))X - Place for payments (page 5, clause 1(g))X - Place of business of bank (page 3, clause 1(d))X | Australian Dollar If nothing stated, that of the jurisdiction where the site is located X If nothing stated, the Principal’s address X If nothing stated, that of the jurisdiction where the site is located X |

| 10 | Bills of quantities (subclause 2.2) X - Alternative applying (subclause 2.2) X - If Alternative 2 applies, is the bill of quantities to be priced? (subclause 2.2) X - Lodgement time (subclause 2.3(b)) X | Alternative 2 If nothing stated, Alternative 1 applies X No (delete one) If neither deleted, the bill of quantities shall not be priced X Tender submission If nothing stated, 28 days after date of acceptance of tender |
| --- | --- | --- |
| 11 | Quantities in schedule of rates, Limits of accuracy (subclause 2.5(b)) X | Upper Limit: Not Applicable Lower Limit: Not Applicable |
| 12 | Provisional sum, Percentage for profit and attendance (clause 3) | 10% |
| 13 | Contractor’s security - Form (clause 5) X - Amount or maximum percentage of contract sum (clause 5) X - If retention moneys, percentage of each progress certificate (clause 5 and subclause 37.2) X - Time for provision (except for retention moneys) (clause 5) X - Additional security for unfixed plant and materials (subclauses 5.4 and 37.3) X - Contractor’s security upon certificate of practical completion is reduced by (subclause 5.4) X | Retention 5% If nothing stated, 5% of the contract sum X 10% If nothing stated, 10%, until the limit in item 13(b) X Not Applicable If nothing stated, within 28 days after date of acceptance of tender X Not Applicable $ 50% of amount held If nothing stated, 50% of amount held X |

| 14 | Principal’s Security - Form (clause 5) X - Amount or maximum percentage of contract sum (clause 5) XX - Time for provision (clause 5) XX - Principal’s security upon certificate of practical completion is reduced by (subclause 5.4) | Not Applicable Not Applicable If nothing stated, nil X Not Applicable If nothing stated, within 28 days after date of acceptance of tender X Not Applicable % of amount held If nothing stated, 50% of amount held X |
| --- | --- | --- |
| 15 | Principal-supplied documents (subclause 8.2) X | Document No. of copies X 1. As per Tender Documentation 1 2. 3. 4. 5. 6. If nothing stated, 5 copies of the drawings, specification, bill of quantities or schedule of rates (if any) X |
| 16 | Time for Superintendent’s direction about documents (subclause 8.3) X | 14 days If nothing stated, 14 days X |
| 17 | Subcontract work requiring approval (subclause 9.2) X | All subcontract work |
| 18 | Novation (subclause 9.4) X | Subcontractor Particular part of WUC X Not Applicable Selected subcontractor Particular part of WUC X Not Applicable |

| 19 | Legislative requirements - Those excepted (subclause 11.1) X - Identified WUC (subclause 11.2(a)(ii)) X | All WUC |
| --- | --- | --- |
| 20 | Insurance of the Works (clause 16) X - Alternative applying If Alternative 1 applies - Provision for demolition and removal of debris - Provision for consultants’ fees - Value of materials or things to be supplied by the Principal - Additional amount or percentage | Alternative 1 If nothing stated, Alternative 1 applies X $0.00 OR % of the contract sum $0.00 OR % of the contract sum NA $0.00 OR % of the total of paragraphs (a) to (d) in clause 16 |
| 21 | Public liability insurance (clause 17) X - Alternative applying If Alternative 1 applies - Amount per occurrence shall be not less than | Alternative 1 If nothing stated, Alternative 1 applies X $20,000,000 (twenty million dollars) If nothing stated, then not less than the contract sum X |
| 22 | Time for giving possession (subclause 24.1) X | TBC in Letter of Award - Please note: Contractor shut down: Christmas holidays 19th December 2026 – 4th January 2027. - Contractor re-take possession site: 5th January 2027. If nothing stated, 14 days X |
| 23 | Qualifying causes of delay Causes of delay for which EOTs will not be granted (page 3, paragraph (b)(iii) of X clause 1 and subclause 34.3) X | None |
| 24 | Liquidated damages, rate (subclause 34.7) X | $1000 per day |
| 25 | Bonus for early practical completion (subclause 34.8) X - Rate - Limit | Nil per day $ per day $ OR % of contract sum If nothing stated, there is no waiver X |
| 26 | Delay damages, other compensable causes (page 1, clause 1 and subclause 34.9) X |  |
| 27 | Defects liability period (clause 35) X | 12 months If nothing stated, 12 months X |
| 28 | Progress Claims (subclause 37.1) X - Times for progress claims OR - Stages of WUC for progress claims | once each month for WUC done to the 25th day of that month |
| 29 | Unfixed plant and materials for which payment claims may be made (subclause 37.3) X | Nil |
| 30 | Interest rate on overdue payments (subclause 37.5) X | 6% per annum If nothing stated, 18% per annum X |

| 31 | Time for Principal to rectify inadequate possession (subclause 39.7) X | 14 days If nothing stated, 14 days X |
| --- | --- | --- |
| 32 | Arbitration (subclause 42.3) X - Person to nominate an arbitrator - Rules for arbitration - Appointing Authority under UNCITRAL Arbitration Rules | If no-one stated, the President of the Institute of X Arbitrators & Mediators Australia X If nothing stated: X - Rules 5-18 of the Rules of The Institute of Arbitrators, Australia X for the Conduct of Commercial Arbitrations; X OR - If one or more of the parties are nationals of and habitually resident in, incorporated in, or where the central management and control is X excised in, different countries as between the parties, the UNCITRAL X Arbitration Rules shall apply and the appointing authority shall be the X person provided in Item 32(c) X If no-one stated, the President of the Institute of X Arbitrators & Mediators Australia X |